## project_plan
Agile project plan
| Project Name | travel any time
| Project Manager | Alaa rafat
| product owner | Eman reda
| Scrum master | Ereny karam
| Start Date | 2018-11-03
| End Date | 2018-10-05
| Task | Responsible | Start | End | Days | Status
| Agree on objectives | Ereny karam | 2018-11-03 | 2018-12-03 | 1 | Complete
| Requeriment gathering | Eman reda | 2018-12-03 | 19/3 | 7 | Complete
| Design Gui | Alaa rafat | 21/3 | 31/3 | 10 | In progress
| Code | Alaa rafat | 21/3 | 31/3 | 10 | In progress
| Code review | Moamen | 2018-01-04 | 2018-04-04 | 3 | Not started
| Testing | Youseif | 2018-05-04 | 2018-07-04 | 2 | In progress
| Implemintation | Zainab | 2018-08-04 | 16/4 | 6 | Not started
| SystemTesting | Eman reda | 17/4 | 20/4 | 3 | Not started
| Maintenance | Ereny karam | 21/4 | 2018-08-05 | optional | Not started
| Launch |  | 2018-09-05 | 2018-10-05 | 1
Agile product Backlog
|  |  |  | TaskName |  | priority | Status | Assigned to sprint
|  |  |  | sprint 1 |  | High | complete | yes
|  |  |  | log_in |  | medium | complete | yes
|  |  |  | sign_in |  | medium | complete | yes
|  |  |  | sprint 2 |  | High | in progress | yes
|  |  |  | select payment methods |  | High | Not started | No
|  |  |  | Get client card information if pay online |  | Low | Not started | No
|  |  |  | sprint 3 |  | medium | Not started | No
|  |  |  | Get company’s offers |  | medium | Not started | No
|  |  |  | Send massage to the main center |  | medium | Not started | No
|  |  |  | sprint 4 |  | Low | Not started | No
|  |  |  | Get map clarify |  | Low | Not started | No
|  |  |  | customer evaluation |  | Low | Not started | No
Idle work | Idle work |  |  |  | Fudge factor |  |  |  |  | project velocity
| 4 weeks |  |  |  |  | 2 weeks |  |  |  |  | 50%
Team organization
| features | identify | role |  | Responsibility |  |  |  | start time | end time
| login | design interface | alaa rafat |  | design the gui for the login page make sure it match with the user needs |  |  |  | 2018-03-11 | 14/3 |  | team manager |  | alaa rafat
|  | code writer | eman reda |  | write the code to enable the design |  |  |  | 2018-03-11 | 15/3 |  | scrum master |  | ereny karam
|  | tester | ereny karam |  | check the whole feature the code and the dsign |  |  |  | 2018-03-15 | 16/3 |  | product owner |  | eman reda
| sign up | design interface | zainab |  | design the gui for the login page make sure it match with the user needs |  |  |  | 2018-03-11 | 14/3 |  | scrum team |  | yousef
|  | code writer | moamen |  | write the code to enable the design |  |  |  | 2018-03-11 | 15/3 |  |  |  | zainab
|  | tester | yousef |  | check the whole feature the code and the dsign |  |  |  | 2018-03-15 | 16/3 |  |  |  | moamen
| select payment method | design interface | ereny karam |  | design the gui for the login page make sure it match with the user needs | [6 empty] | system tester |  | eman reda
|  | code writer | eman reda |  | write the code to enable the design
|  | tester | alaa rafat |  | check the whole feature the code and the dsign
| get client info if paymnet online | design interface | moamen |  | design the gui for the login page make sure it match with the user needs
|  | code writer | yousef |  | write the code to enable the design
|  | tester | zainab |  | check the whole feature the code and the dsign | [6 empty] | database adminstartor | desgin table
| company's offer | design interface | [10 empty] | fill tables
|  | code writer | [10 empty] | test
tester
| send msg | design interface
code writer
database adminstrator
tester
| map clarify | database adminstrator
code writer
design interface
tester
| customer evaluation | design interface
code writer
tester
database adminstrator
Sprint Backlog
| Duration: Two weak estimate. | [5 empty] | Duration:Two weak estimate.
| Goal : to get the site open to finish your task and to save your information for booking | [5 empty] | Goal : to get the site open to finish your task and to save your information for booking
| Analysis (Collect Data) |  | log in |  | Sprint (1) |  | Analysis (Collect Data) | Payment Methods | Sprint (2)
| Design (make skatch to page) | [5 empty] | Design (make skatch to page)
| implimentation(Codng) | [5 empty] | implimentation(Codng)
| Testing(Trace the code) | [5 empty] | Testing(Trace the code)
| Modification | [5 empty] | Modification
| Analysis (Collect Data) |  | sign up |  |  |  | Analysis (Collect Data) | pay online
| Design (make skatch to page) | [5 empty] | Design (make skatch to page)
| implimentation(Codng) | [5 empty] | implimentation(Codng)
| Testing(Trace the code) | [5 empty] | Testing(Trace the code)
| Modification | [5 empty] | Modification
| Duration: Two weak estimate. | [5 empty] | Duration: Two weak estimate.
| Goal : to get the site open to finish your task and to save your information for booking | [5 empty] | Goal : to get the site open to finish your task and to save your information for booking
| Analysis (Collect Data) |  | commpanies offers |  | Sprint (3) |  | Analysis (Collect Data) | map clarify | Sprint (4)
| Design (make skatch to page) | [5 empty] | Design (make skatch to page)
| implimentation(Codng) | [5 empty] | implimentation(Codng)
| Testing(Trace the code) | [5 empty] | Testing(Trace the code)
| Modification | [5 empty] | Modification
| Analysis (Collect Data) |  | service |  |  |  | Analysis (Collect Data) | customer evaluation
| Design (make skatch to page) | [5 empty] | Design (make skatch to page)
| implimentation(Codng) | [5 empty] | implimentation(Codng)
| Testing(Trace the code) | [5 empty] | Testing(Trace the code)
| Modification | [5 empty] | Modification
*) Planning of the project: we will identify all structure of the project plan.
· To plan a project, we need to be sure that we have captured all of the
· Deliverables and tasks that make up the finished product. Get our team together and ask them to spend 10-20 mins listing out all of the tasks to identify
· The requirement correctly.
Project Resources: -
1- stakeholders
2-customers
3-project manager
4-Developer
5-Designer
6- Tester

## Budget
Budget
| project summary | status | percentage complete | planned start date | end date | estimate labor ($)
| sprint 1 | complete | 1 | 11\3 | 24\3 | 1000
| log in (home page). | finished |  | 11\3 | 24\3 | 500
| Sign in (book page). | finished |  | 11\3 | 24\3 | 500
| sprint 2 | start | 20% | 25\3 | 8\4
| select payment methods | in progress | 10% | 25\3 | 8\4 | 0
| Get client card information if pay online | in progress | 10% | 25\3 | 8\4 | 0
| sprint 3 | not started |  | 9\4 | 13\4
| Get company’s offers | not started |  | 9\4 | 13\4
| Send massage to the main center . | not started |  | 9\4 | 13\4
| sprint 4 | not started |  | 14\4 | 28\4
| Get map clarify | not started |  | 14\4 | 28\4
| customer evaluation | not started |  | 14\4 | 28\4

## Risks
Risk
# | Risk | risk rating | Actions to Minimise Risk
1 | data/system faliure | medium | backup the system
2 | hacker/virus | medium | make the system securtiy
3 | some of defects need to re-design | high
4 | the server for the project have not been concerned | high | buy and build a new server
5 | Requirements and developed functions do not match | low | involve user in the project
6 | problem with the time | high | The time should be determined before starting the project